## Project Timeline
12 week project timeline
Start Date: | 2019-09-05
| week 1-Week 4 | [6 empty] | Week 5-Week6 | [6 empty] | week 7-Week 8 | [6 empty] | week 9-Week 12 | [6 empty] | Status:
| sep | [6 empty] | sep | [6 empty] | sep | [6 empty] | sep |  |  |  |  | oct
| tue | wed | thur | fri | sat | sun | mon | tue | wed | thur | fri | sat | sun | mon | tue | wed | thur | fri | sat | sun | mon | tue | wed | thur | fri | sat | sun | mon
Assigned to: | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | 2019-10-02
EDX learner | 2019-09-05: Canvanizer assessment | completed
completed
EDX learner | 2019-09-12: Video presentation | completed
EDX learner | 2019-09-19: Market Reasech and costing | in progress
EDX learner | 2019-09-26: Prototype and Final report | not started

## Sheet1
WBS NO. | Activity | earliest start date | Latest End date | Resources | Timelines | Risk assetment
1 | Project management
2 | Canvanizer | 2019-07-23 | 2019-08-07 | Time and Computer | Week 3-Week 4
3 | Video presentation | 2019-08-08 | 2019-08-23 | Time and Video caputing equipment | Week 4-Week 6
4 | Market research cost report | 2019-08-24 | 2019-09-08 | Time and research cost | Week 7-Week 8
5 | Prototype | 2019-09-01 | 2019-09-25
5.1 | Process mapout | 2019-09-01 | 2019-09-02 | Paper
5.2 | Identify the control system | 2019-09-03 | 2019-09-04 | paper
6 | Required devices to be connected
6.1 | Identify the sensor |  |  | Inductive and conductive proximity sensor and raspberrypi camera
6.2 | Identify the Actuator |  |  | Servo motor 180 degree rotation
6.3 | Identify the intermediate device |  |  | Arduino mega and Raspberrypi
7 | IOT protocol consderations |  |  | Range within the shop
8 | IoT protocol choice |  |  | Wifi
8.1 | Type generated |  |  | Volume, limited data range, partly processed in fog, analysis shared on web
8.2 | Storage solution |  |  | Local server, backed up
8.3 | analysis overview |  |  | Identify the type of material and report to the device for functioning
9 | Programming Required
9.1 | device function |  |  | programming to record the type of material. Holds data for 24 hours unless in contact with wifi when it uploads data.
9.2 | networking requirment |  |  | Data from sensor directed to wifi on AWS IOT.AWS Iot send data to device via wifi to direct actuator
9.3 | data management |  |  | Data needs algorithm to identify material that suggests whether the material is metallic or non metallic,help device to seprate the material in different bin
10 | Security and privacy consideration
10.1 | deivce |  |  | Need to be secured from water,dust
10.2 | network |  |  | Resisit the wifi coverge outside the shop and stop being connected that wifi to other
10.3 | data |  |  | Protect historical data from being lost, stolen or ransomed, guard against re-setting of algorithm so shows all material are metallic or all non metallic